GUJRAAT STATE POWER CORPORATION LIMITED

(A Government of Gujraat Undertaking)

TENDER DOCUMENT
Design, Supply, Installation, Testing & Commissioning of 5 MW Grid-Connected Solar Photovoltaic Power Plant
with 5-Year Comprehensive Operation & Maintenance

| Field | Details |
| --- | --- |
| Tender Reference No. | GSPCL/SOLAR/2026/EPC-014 |
| Issuing Authority | Gujraat State Power Corporation Limited (GSPCL) |
| Mode of Tendering | Two-Envelope System (Technical Bid + Financial Bid), e-Procurement Portal |
| Tender Fee | ₹10,000 (Non-refundable) |
| Earnest Money Deposit (EMD) | ₹75,00,000 (Refundable, or 2% of quoted Bid Value, whichever is higher) |
| Bid Validity | 120 days from the date of Financial Bid opening |
| Date of Issue | 01-Feb-2026 |
| Pre-Bid Meeting | 12-Feb-2026, 11:00 AM, GSPCL Head Office, Gandhinagar |
| Last Date for Submission | 10-Mar-2026, 5:00 PM (IST) |
| Technical Bid Opening | 11-Mar-2026, 11:00 AM (IST) |
| Financial Bid Opening | To be intimated to technically qualified bidders only |

# 1. Scope of Work

The Contractor shall be responsible for the complete Engineering, Procurement and Construction (EPC) of a 5 MW (AC) Grid-Connected Solar Photovoltaic Power Plant, on a turnkey basis, at the designated site situated at Village Bhachau, Kutch District, Gujraat, including but not limited to:

- Site survey, geotechnical investigation, and detailed engineering design

- Supply of PV modules, inverters, mounting structures, cabling, and Balance of System (BOS) components

- Civil, structural, and electrical works including internal roads, drainage, and fencing

- Construction of 33 kV switchyard and interconnection with the State grid substation

- Installation of SCADA-based remote monitoring and weather station

- Testing, commissioning, and synchronization with the grid

- Comprehensive Operation & Maintenance (O&M) for a period of 5 years post-Commercial Operation Date (COD)

- Training of GSPCL personnel and handover of As-Built documentation

# 2. Eligibility Criteria (Pre-Qualification)

Bidders must satisfy ALL of the following criteria to be considered eligible. Non-compliance with any mandatory criterion shall render the bid liable for rejection at the eligibility screening stage, without proceeding to technical evaluation.

| S.No. | Criteria | Requirement |
| --- | --- | --- |
| EC-1 | Average Annual Turnover | Minimum ₹15,00,00,000 (₹15 Crore) in each of the last 3 financial years (FY 2022-23, 2023-24, 2024-25), certified by Chartered Accountant |
| EC-2 | Relevant Experience | Successful completion (COD achieved) of at least 3 solar PV EPC projects of 2 MW or above each, OR at least 1 project of 5 MW or above, in the last 5 years |
| EC-3 | Net Worth | Positive net worth as per the latest audited financial statement |
| EC-4 | Quality Certifications | Valid ISO 9001:2015 (Quality), ISO 14001:2015 (Environment) and ISO 45001:2018 (OH&S) certificates |
| EC-5 | Statutory Registrations | Valid PAN, GST Registration, and EPFO Registration |
| EC-6 | Blacklisting Declaration | Self-certified undertaking that the bidder is not blacklisted / debarred by any Central/State Government or PSU as on the bid due date |
| EC-7 | EMD Submission | EMD of ₹75,00,000 in the form of Bank Guarantee / Demand Draft, valid for 180 days |

# 3. Technical Requirements

| S.No. | Parameter | Minimum Requirement |
| --- | --- | --- |
| TR-1 | PV Module Type | Tier-1 Mono PERC / TOPCon, module efficiency ≥ 20.5%, unit rating ≥ 540 Wp |
| TR-2 | Module Warranty | 25 years linear performance warranty (≥ 80.7% output at end of Year 25) |
| TR-3 | Inverter Type | String or Central Inverter, minimum efficiency 98.0% |
| TR-4 | Inverter Warranty | Minimum 5 years comprehensive warranty |
| TR-5 | Mounting Structure | Hot-dip galvanized MS/GI fixed-tilt or single-axis tracker structure, design life 25 years |
| TR-6 | Grid Interconnection | 33 kV interconnection with State grid, as per CEA/State Discom norms |
| TR-7 | Monitoring | SCADA-based real-time remote monitoring with weather station (irradiance, temperature, wind) |
| TR-8 | Land Requirement | Approximately 25 acres (provided by GSPCL; bidder to confirm layout feasibility) |
| TR-9 | Performance Ratio (PR) | Minimum 80% in the first year of operation, guaranteed |
| TR-10 | O&M Period | 5 years comprehensive O&M including manpower, spares, and insurance |

# 4. Commercial Requirements

- Prices shall be quoted on a firm, fixed-price, turnkey basis (FOR Site) inclusive of all duties except GST, which shall be shown separately.

- Performance Bank Guarantee (PBG) of 5% of the total Contract Value shall be submitted within 15 days of Letter of Intent (LOI), valid till expiry of Defect Liability Period.

- Payment shall be released strictly as per the Milestone Payment Schedule (Section 6).

- Prices quoted shall remain firm throughout the contract period; no price escalation shall be permitted except statutory tax changes.

# 5. Evaluation Criteria

Evaluation shall be conducted in three sequential stages. Bidders failing at any stage shall not proceed to the subsequent stage.

## Stage 1: Eligibility Screening

Bids shall be screened against the mandatory Eligibility Criteria (Section 2) on a Compliant / Non-Compliant basis. Only fully eligible bidders shall proceed to Stage 2.

## Stage 2: Technical Evaluation (100 marks; minimum qualifying score 60 marks)

| Criteria | Max Marks |
| --- | --- |
| Relevant Project Experience & Track Record | 20 |
| Technical Design, Equipment Specification & Compliance | 25 |
| Project Execution Methodology & Schedule | 15 |
| Manpower, Equipment & Financial Capacity | 10 |
| Technical Compliance to Section 3 Requirements | 20 |
| Presentation & Documentation Quality | 10 |

## Stage 3: Financial Evaluation

Financial Bids of only technically qualified bidders (score ≥ 60/100) shall be opened. The bidder quoting the Lowest Evaluated Total Bid Value (L1) among technically qualified bidders shall ordinarily be recommended for award, subject to the Evaluation Committee's assessment of any technical deviations, value-additions, or price normalization adjustments.

# 6. Pricing / Bid Value Structure & Milestone Payment Schedule

Bidders shall quote prices strictly in the format below (Engineer's Estimate shown as reference; NOT to be disclosed to bidders during bidding):

| Component | Engineer's Estimate (₹) | Payment Milestone (% of component value) |
| --- | --- | --- |
| Supply of PV Modules | ₹7,40,00,000 | 40% on delivery, 60% on commissioning |
| Supply of Inverters | ₹1,85,00,000 | 40% on delivery, 60% on commissioning |
| Balance of System (Structures, Cables, BOS) | ₹2,85,00,000 | 30% on delivery, 70% on commissioning |
| Civil & Structural Works | ₹1,65,00,000 | As per work completion (milestone-based) |
| Electrical Works (Switchyard, Transformer, Cabling) | ₹2,20,00,000 | As per work completion (milestone-based) |
| Installation, Testing & Commissioning | ₹90,00,000 | 100% on successful COD |
| SCADA & Monitoring System | ₹40,00,000 | 100% on commissioning |
| Comprehensive O&M (5 Years) | ₹1,20,00,000 | Quarterly in arrears over 5 years |
| Total Base Price (Estimate) | ₹18,45,00,000 | — |
| GST @ 13.8% (effective, blended) | ₹2,54,61,000 | As applicable |
| Total Bid Value (Estimate, incl. GST) | ₹20,99,61,000 | — |

# 7. Project Milestones & Deliverables

| Milestone | Deliverable | Timeline (from LOI date) |
| --- | --- | --- |
| M1 - Mobilization | Mobilization of team, insurance, PBG submission | T + 15 days |
| M2 - Design Approval | Detailed engineering design & drawings approved by GSPCL | T + 45 days |
| M3 - Land Development | Site clearance, fencing, internal roads complete | T + 90 days |
| M4 - Module & Equipment Delivery | PV modules, inverters, BOS delivered to site | T + 150 days |
| M5 - Structure Erection & Module Mounting | Mechanical installation complete | T + 210 days |
| M6 - Electrical BOP & Switchyard | Cabling, transformer, switchyard complete | T + 240 days |
| M7 - Grid Synchronization & Testing | Successful test synchronization with grid | T + 260 days |
| M8 - Commercial Operation Date (COD) | Plant achieves full 5 MW output, handover to GSPCL | T + 270 days (9 months) |
| M9 - Defect Liability Period | 12 months post-COD, followed by 5-year O&M | T + 270 to T + 630 days |

# 8. General Terms & Conditions

- Bid Validity: 120 days from Financial Bid opening date.

- Delivery/Completion Period: 9 months (270 days) from date of LOI, achieving COD.

- Liquidated Damages (LD): 0.5% of Contract Value per week of delay, subject to a maximum cap of 10% of Contract Value.

- Defect Liability Period (DLP): 12 months from COD, followed immediately by the 5-year O&M contract.

- Force Majeure: As per standard GSPCL General Conditions of Contract (GCC), Clause 22.

- Dispute Resolution: Arbitration under the Arbitration & Conciliation Act, 1996, seat at Gandhinagar; Gujraat courts shall have exclusive jurisdiction.

- Insurance: Contractor to maintain Contractor's All Risk (CAR) Insurance and Third-Party Liability Insurance for the full contract duration.

- Taxes: GST shall be charged extra at applicable rates; all other duties, cess and levies to be included in quoted price.

- GSPCL reserves the right to accept or reject any or all bids without assigning any reason, and to waive minor infirmities/deviations at its sole discretion.

# 9. Bid Submission Requirements

Bids shall be submitted online via the GSPCL e-Procurement Portal in two separate envelopes (digitally sealed):

## Envelope 1 - Technical Bid (must NOT contain any price information)

- Bid Submission Form (Annexure-A), duly signed and sealed

- EMD instrument (Bank Guarantee / DD)

- Eligibility documents as per Section 2 (turnover certificates, experience certificates, ISO certificates, registrations)

- Blacklisting declaration (self-certified, notarized)

- Technical Proposal: design basis, equipment datasheets, execution methodology, project schedule (bar chart), manpower deployment plan, list of key equipment/machinery

- Power of Attorney authorizing the signatory

## Envelope 2 - Financial Bid

- Price Schedule in the format prescribed in Section 6, component-wise, with Total Base Price, GST, and Total Bid Value clearly indicated

- Financial Bid Form (Annexure-B), duly signed and sealed

All pages of the bid must be signed and stamped by the authorized signatory. Bids submitted after the due date/time, or in incomplete/incorrect format, shall be summarily rejected. All correspondence shall be in English.