## Slide 1
SOLSTICE ENERGY COOPERATIVE
Office of Power Supply & Renewable Programs
REVISED ISSUE – SUPERSEDES RFP-SEC-2026-0029
VENDOR PRE-BID BRIEFING
Community Solar, Battery Storage & EV Charging Infrastructure Program
Vendor briefing for prospective EPC bidders
RFP Number | RFP-SEC-2026-0029-R1
Issue Date | May 19, 2026
Proposal Deadline | June 30, 2026, 3:00 PM CT

## Slide 2
Agenda
About Solstice Energy Cooperative
Project Objectives
Scope of Work
Technical Requirements Overview
EV Charging & Interconnection Requirements
Eligibility Criteria
Project Timeline
Evaluation Criteria
Commercial Terms & Next Steps

## Slide 3
About Solstice Energy Cooperative
Member-owned electric cooperative serving approximately 41,000 members across an expanded 6-county service territory, following the March 2026 addition of the Hartwell service area.
Board of Directors approved a Community Solar + Battery Storage initiative in December 2025, and expanded the program scope in April 2026 to include EV fast-charging infrastructure.
Program goal: add 14 MW of community solar generation, 10 MWh of battery storage, and a public EV fast-charging hub.
This RFP solicits a qualified EPC (Engineer-Procure-Construct) contractor for the expanded program.

## Slide 4
Project Objectives
Add 14 MW of community solar generation capacity at the Co-op's Meadowbrook site.
Add 10 MWh of battery energy storage for peak shaving and grid support.
Launch a member subscription program allowing members to subscribe to community solar output.
Deploy a public DC fast-charging hub at the Meadowbrook site to serve members and the traveling public.
Achieve commercial operation date (COD) by Q2 2028.

## Slide 5
Scope of Work
Design, procure, and construct a 14 MW solar array at the Meadowbrook site.
Design, procure, and install a 10 MWh battery energy storage system (BESS).
Design, procure, and install a 6-stall DC fast-charging hub at the Meadowbrook site.
Interconnect the solar, BESS, and EV charging systems to the Co-op's existing 34.5kV distribution system.
Implement a member subscription billing platform integrated with the Co-op's billing system.
Provide 5 years of operations and maintenance (O&M) services following commercial operation.

## Slide 6
Technical Requirements Overview
Solar modules: Tier 1 manufacturer, minimum 21% module efficiency.
Inverters: UL 1741-SA certified with grid-support functions (volt-VAR, frequency-watt).
Battery energy storage: UL 9540 certified, minimum 6-hour discharge duration.
SCADA integration with the Co-op's existing Advanced Distribution Management System (ADMS).
Cybersecurity practices for all networked control systems aligned with NERC CIP guidance.

## Slide 7
EV Charging & Interconnection Requirements
Six DC fast-charging stalls, each rated at a minimum of 150 kW.
OCPP 2.0.1 protocol compliance for charge point management and payment integration.
Charging hub must support future expansion to 12 stalls without additional transformer upgrades.
Dedicated metering for the EV charging hub, separate from the solar and BESS metering points.
This slide is new in this revision — no equivalent content existed in the original briefing deck.

## Slide 8
Eligibility Criteria
Criterion | Minimum Requirement
Utility-scale solar EPC experience | 7 years
Minimum annual revenue | $40,000,000
Reference projects (5 MW+) | 4, completed within 5 years, ≥1 incl. EV charging
Insurance (general / professional liability) | $8,000,000 / $3,000,000
Performance bond | 65% of contract value

## Slide 9
Project Timeline
Milestone | Date
RFP Reissue Date | May 19, 2026
Virtual Site Walkthrough (recorded, on-demand) | June 2, 2026
Vendor Q&A Deadline | June 9, 2026
Proposal Submission Deadline | June 30, 2026
Contract Award | September 2026
Notice to Proceed (NTP) | November 2026
Commercial Operation Date (COD) | Q2 2028

## Slide 10
Evaluation Criteria
Criterion | Weight
Technical Solution & Design | 25 points
Vendor Experience & References | 15 points
Cost | 30 points
Schedule | 10 points
O&M Plan | 10 points
EV Charging Design | 10 points

## Slide 11
Commercial Terms & Next Steps
Contract structure: fixed-price EPC contract.
Estimated total project cost: $38,000,000 – $46,000,000.
Payment milestones tied to design completion, procurement, construction progress, and COD.
Warranty period: 3 years following commercial operation.
Liquidated damages apply for delays past the contractual COD, at an increased daily rate reflecting the expanded scope.
Next step: submit written questions by the Q&A deadline; proposals due June 30, 2026.

## Slide 12
Questions & Contact
Thank you for your interest in Solstice Energy Cooperative's Community Solar, Battery Storage & EV Charging Infrastructure Program. Please direct all questions to the contact below in writing.
Issuing Officer | Priya Patel
Title | Senior Director of Power Supply & Grid Modernization
Email | ppatel@solsticeenergycoop.org
Phone | (605) 555-0164