## Slide 1
SOLSTICE ENERGY COOPERATIVE
Office of Power Supply & Renewable Programs
ORIGINAL ISSUE
VENDOR PRE-BID BRIEFING
Community Solar & Battery Storage Program
Vendor briefing for prospective EPC bidders
RFP Number | RFP-SEC-2026-0029
Issue Date | March 3, 2026
Proposal Deadline | April 14, 2026, 3:00 PM CT

## Slide 2
Agenda
About Solstice Energy Cooperative
Project Objectives
Scope of Work
Technical Requirements Overview
Eligibility Criteria
Project Timeline
Evaluation Criteria
Commercial Terms & Next Steps

## Slide 3
About Solstice Energy Cooperative
Member-owned electric cooperative serving approximately 38,000 members across a 5-county service territory.
Board of Directors approved a Community Solar + Battery Storage initiative in December 2025.
Program goal: add 12 MW of community solar generation and 8 MWh of battery storage capacity.
This RFP solicits a qualified EPC (Engineer-Procure-Construct) contractor for the program.

## Slide 4
Project Objectives
Add 12 MW of community solar generation capacity at the Co-op's Meadowbrook site.
Add 8 MWh of battery energy storage for peak shaving and grid support.
Launch a member subscription program allowing members to subscribe to community solar output.
Achieve commercial operation date (COD) by Q4 2027.

## Slide 5
Scope of Work
Design, procure, and construct a 12 MW solar array at the Meadowbrook site.
Design, procure, and install an 8 MWh battery energy storage system (BESS).
Interconnect the solar and BESS systems to the Co-op's existing 34.5kV distribution system.
Implement a member subscription billing platform integrated with the Co-op's billing system.
Provide 5 years of operations and maintenance (O&M) services following commercial operation.

## Slide 6
Technical Requirements Overview
Solar modules: Tier 1 manufacturer, minimum 21% module efficiency.
Inverters: UL 1741-SA certified with grid-support functions (volt-VAR, frequency-watt).
Battery energy storage: UL 9540 certified, minimum 4-hour discharge duration.
SCADA integration with the Co-op's existing Advanced Distribution Management System (ADMS).

## Slide 7
Eligibility Criteria
Criterion | Minimum Requirement
Utility-scale solar EPC experience | 5 years
Minimum annual revenue | $25,000,000
Reference projects (5 MW+) | 3, completed within 5 years
Insurance (general / professional liability) | $5,000,000 / $2,000,000
Performance bond | 50% of contract value

## Slide 8
Project Timeline
Milestone | Date
RFP Issue Date | March 3, 2026
Optional Site Visit (Meadowbrook site) | March 17, 2026
Vendor Q&A Deadline | March 24, 2026
Proposal Submission Deadline | April 14, 2026
Contract Award | June 2026
Notice to Proceed (NTP) | August 2026
Commercial Operation Date (COD) | Q4 2027

## Slide 9
Evaluation Criteria
Criterion | Weight
Technical Solution & Design | 30 points
Vendor Experience & References | 20 points
Cost | 30 points
Schedule | 10 points
O&M Plan | 10 points

## Slide 10
Commercial Terms & Next Steps
Contract structure: fixed-price EPC contract.
Estimated total project cost: $28,000,000 – $34,000,000.
Payment milestones tied to design completion, procurement, construction progress, and COD.
Warranty period: 2 years following commercial operation.
Liquidated damages apply for delays past the contractual COD.
Next step: submit written questions by the Q&A deadline; proposals due April 14, 2026.

## Slide 11
Questions & Contact
Thank you for your interest in Solstice Energy Cooperative's Community Solar & Battery Storage Program. Please direct all questions to the contact below in writing.
Issuing Officer | Derek Simmons
Title | Director of Power Supply
Email | dsimmons@solsticeenergycoop.org
Phone | (605) 555-0121